SITESYNC AI

Schedule Engine

Strategic Implementation Plan

Building the World’s Most Intelligent Construction Scheduling Platform

Prepared: April 2026

Classification: Internal — Strategic

Version: 1.0

# Executive Summary

SiteSync AI is building a construction scheduling platform that will replace Oracle Primavera P6 as the industry standard. Not by copying P6’s feature set, but by making the hard things automatic and the complex things simple. This plan lays out the path from our current foundation—a production-quality Gantt UI with a working CPM engine—to a scheduling platform that no General Contractor has ever seen.

The core thesis: P6 is the most powerful scheduling tool in construction, and also the most hated. Every superintendent and PM knows they need it and resents using it. The opportunity is not to build P6 but prettier—it’s to build a system that is smarter than any human scheduler while being simpler than a spreadsheet to operate.

What Already Exists

The codebase audit reveals a strong foundation: a full CPM engine with forward/backward pass supporting all four dependency types (FS/SS/FF/SF) with lag; P6 XER and MSP XML import/export; a custom high-performance Gantt with virtual scrolling, dependency arrows, baseline overlays, and critical path highlighting; KPI calculations (SPI, variance, float consumed); plus AI risk detection, a lookahead board, and real-time Supabase subscriptions.

The Six Phases

| Phase | Name | Headline | Timeline |
| --- | --- | --- | --- |
| 0 | Foundation Polish | WBS hierarchy + visual completeness | Weeks 1–4 |
| 1 | Schedule Intelligence | Auto quality checks — the killer feature | Weeks 5–10 |
| 2 | Calendar & Weather | Real-world time awareness | Weeks 11–16 |
| 3 | Claims & Analysis | TIA, fragnets, narrative reports | Weeks 17–26 |
| 4 | Resource Intelligence | Leveling, histograms, EVM | Weeks 27–38 |
| 5 | AI Scheduling Brain | Predictive + generative — the moat | Weeks 39–52+ |

The single most important insight: Phase 1 (Schedule Intelligence) is the breakout moment. No existing tool—not P6, not Procore, not MS Project—automatically detects open ends, negative float, out-of-sequence progress, and dangling activities, then guides the PM to fix them. That feature alone is worth the switch.

# Design Principles

Every decision follows five principles. When they conflict, the order is the tiebreaker.

- Correctness before beauty. A schedule that computes wrong dates is worthless. The CPM engine must match P6 output as ground truth.

- Automate the expertise. The best PMs check for open ends and negative float before submitting. SiteSync does it automatically, for every PM, every time.

- Import is the front door. No GC rebuilds from scratch. They import a P6 XER file. That experience determines whether they stay.

- Ship value every phase. No infrastructure-only phases. Every phase delivers something a superintendent can use on a live jobsite.

- The Gantt is the product. Not a dashboard, not a sidebar. The Gantt chart is where PMs live 8 hours a day. Every pixel matters.

# Current State Audit

Full codebase audit across database schema, CPM engine, Gantt chart, import/export, and UI:

| Capability | Status | Details |
| --- | --- | --- |
| CPM Engine (fwd/bwd pass) | BUILT | All 4 dep types + lag. Float calc. 385 lines |
| P6 XER Import/Export | BUILT | XER parser + ERMHDR export. MSP XML + CSV |
| Custom Gantt Chart | BUILT | Virtual scroll, zoom, drag, baseline, dep arrows, milestones |
| KPIs (SPI, variance, float) | BUILT | Schedule variance, SPI, critical path length, float consumed |
| AI Risk Detection | BUILT | Prediction engine for delays, violations, conflicts |
| WBS Hierarchy | MISSING | No parent_id, no indent, no collapse/expand |
| Schedule Quality Checks | MISSING | No open-end detection, no OOS flagging |
| Calendar Engine | MISSING | No multi-calendar, no 6-day weeks, no holidays |
| TIA / Fragnets | MISSING | No what-if engine, no fragnet UI |
| Resource Leveling | MISSING | Single crew only, no histogram, no leveling |
| Float/Lag Visualization | PARTIAL | Computed but not rendered on bars |

Assessment: The foundation is strong. The CPM engine is real, the Gantt is performant, the data pipeline works. What’s missing is the intelligence layer that transforms this from a visualization tool into a scheduling advisor.

PHASE 0  —  Weeks 1–4

Foundation Polish

Before adding new capabilities, close the visual and structural gaps. A GC evaluating SiteSync will import their P6 file and look for three things: Can I see my WBS? Can I see float? Does it feel like a real scheduling tool?

Deliverables

- WBS Hierarchy — Add parent_id to schedule_phases. Indent levels, expand/collapse toggles, summary bars aggregating child ranges. The #1 thing a PM looks for after import.

- Float Visualization — Translucent extension beyond each bar showing available float. Zero-float bars show no extension. Makes float intuitive without numbers.

- Lag Indicators — Dashed segments on dependency arrows showing lag. Negative lag (lead) shown differently.

- Constraint Markers — Pin/lock icons on bars for must-start-on, must-finish-on constraints with tooltips.

- Drag-to-Link — Create dependency links by dragging from one bar’s handle to another. Currently links render but can’t be created via drag.

Success Criteria

- Import 200-activity P6 XER. WBS tree renders correctly with hierarchy, all bars visible, float shown.

- A superintendent who has never used P6 can understand the schedule within 30 seconds.

PHASE 1  —  Weeks 5–10

Schedule Intelligence

This is the breakout feature. No tool—not P6, not Procore, not MS Project—automatically analyzes a schedule for quality problems and tells the PM how to fix them. Every GC knows they should check for open ends and out-of-sequence progress. Most don’t because it requires expert P6 knowledge. SiteSync does it automatically. Every time.

The Schedule Health Engine

A new module (scheduleHealth.ts) running after any change, import, or progress update. Produces a scored HealthReport with categorized findings and one-click fix recommendations.

Quality Checks

- Open Ends — Activities with no successor or predecessor. Suggests: “Task ‘Install Drywall’ has no successor. Should it link to ‘Paint Interior’ (FS)?”

- Negative Float — Activities where late finish < early finish. Traces the constraint chain causing it and shows the PM exactly which path is over-committed.

- Out-of-Sequence Progress — Activities started before predecessors finished. Flags severity and suggests adding a lead, changing relationship type, or acknowledging.

- Dangling Activities — Not connected to project completion through any path. Shows which milestone they should connect to.

- Unreasonable Durations — Zero-day non-milestones, or >20 day activities without WBS breakdown. Suggests splitting.

- Logic Density Score — Percentage of activities with both predecessors and successors. Industry benchmark: >95%.

The Health Panel UI

Collapsible right-side panel showing Schedule Health Score (0–100) with color ring, plus categorized findings. Each finding clickable: highlights the activity in the Gantt and offers a one-click fix button.

Why This Wins

- For PMs: No more schedule rejections from the CM. Submit with confidence every time.

- For owners/CMs: They’ll require GCs to use SiteSync because it guarantees schedule quality. Viral adoption vector.

- For SiteSync: The feature mentioned in every sales call. “It checks your schedule for you.” Sells itself.

PHASE 2  —  Weeks 11–16

Calendar & Weather Engine

Construction doesn’t operate on a 5-day week. Most GCs run 6-day, some go 7-day during crunch. Holiday calendars vary by trade union, region, and contract. A tool assuming Monday–Friday is instantly disqualified. This phase makes SiteSync calendar-aware at every level.

Deliverables

- Project Calendar — Default calendar: work days/week, hours/day, holidays, exceptions. Configurable per-project.

- Resource Calendars — Per-crew calendars overriding project default. Electricians 5-day, concrete 6-day.

- Weather Integration — Connect to forecast APIs. Auto gray-out days where weather prevents exterior work. Generate delay events the CPM engine factors in.

- Calendar-Aware CPM — Count only working days for durations and float. 10-day task on 6-day calendar = fewer calendar days. Where most cloud schedulers fail.

- Non-Work Day Visualization — Gray vertical bands on Gantt for weekends, holidays, weather days. Bars skip over non-work days.

Success Criteria

- 6-day calendar computes 10 working days as 12 calendar days (skipping Sundays). Matches P6 output exactly.

- Weather integration marks upcoming rain days and CPM shifts affected exterior tasks.

PHASE 3  —  Weeks 17–26

Claims & Analysis

This is where the money is. On a 0M project, a 30-day delay can mean 00K+ in liquidated damages. GCs need tools to document, analyze, and defend schedule impacts. P6 supports TIA through manual fragnet insertion—a process requiring a 00/hr scheduling consultant. SiteSync automates it.

Deliverables

- What-If Mode — Toggle creating a temporary schedule fork. All edits non-destructive. Accept or discard when done.

- Fragnet Insertion — Guided workflow: cause, affected activities, duration. System creates delay block, links it, runs CPM.

- Impact Report — Days of extension, critical path shift, affected milestones, before/after Gantt. Exportable as PDF.

- Multiple Baselines — Unlimited snapshots with names and dates. Compare any two side-by-side.

- Narrative Reports — AI-generated summaries: “The project is 42% complete. Three critical activities are delayed 5–8 days due to owner-directed scope change, extending completion from Oct 15 to Oct 23.”

Why This Matters

Current process: hire consultant (50–50/hr), wait 2 weeks, argue methodology. SiteSync does it in 30 seconds, following AACE-standard TIA methodology—without the human error or the invoice.

PHASE 4  —  Weeks 27–38

Resource Intelligence

A schedule without resource loading is a wish list. Resource-loaded schedules tell the truth: can you execute this plan with the crews you have? P6 handles leveling but makes it opaque. SiteSync makes it visual, automatic, and honest.

Deliverables

- Multi-Resource Assignment — Assign multiple crews/equipment with unit allocation. Drag-drop from resource panel onto bars.

- Resource Histogram — Stacked bar chart below Gantt showing utilization per day/week. Over-allocations in red.

- Automatic Leveling — One-click leveling delaying non-critical tasks. Uses float intelligently. Before/after comparison.

- Crew Optimization — AI suggestions: “Add 1 electrician to weeks 12–14 to eliminate over-allocation and save 3 days.”

- Earned Value — Full EVM: BCWS, BCWP, ACWP, SPI, CPI, EAC, ETC, VAC. Trend charts over time.

PHASE 5  —  Weeks 39–52+

AI Scheduling Brain

This is the moat. Phases 0–4 bring feature parity with P6. Phase 5 takes SiteSync somewhere P6 can’t follow. The AI Brain doesn’t replace PM judgment—it augments it with pattern recognition no human can match. A PM who’s done 10 projects knows 10 projects of patterns. SiteSync’s AI knows thousands.

Capabilities

- Logic Gap Detection — ML model trained on construction schedules. “In 94% of similar projects, Rough Electrical depends on Frame Walls. Your schedule is missing this link.” Ghost arrows on Gantt—click to accept.

- Auto-Link Assistant — When adding a new activity, AI suggests predecessors/successors based on name, WBS, trade, and similar projects.

- Delay Risk Prediction — Combines historical data, weather, lead times, permits. Risk scores update daily. High-risk activities highlighted with probability.

- Intelligent Narratives — LLM-generated reports explaining causation chains. Adapts tone for owners (formal), team (concise), subs (scope-specific).

- Schedule Benchmarking — Compare against anonymized benchmarks. “Your concrete sequence is 15% longer than median for similar mid-rise projects.”

- Optimal Sequencing — Given activities, constraints, and resources, compute the sequence minimizing total duration. A starting point better than a blank Gantt.

Guardrails

- Never auto-modify. AI suggests; the PM accepts. Every suggestion shows reasoning.

- Deterministic first, ML second. Quality checks use rules. Predictions use ML. Don’t use ML where rules suffice.

- Confidence scores on everything. PMs trust tools they can verify.

# Competitive Position

After all six phases, SiteSync’s position:

| Capability | P6 | MS Project | Procore | SiteSync | Phase |
| --- | --- | --- | --- | --- | --- |
| Full CPM Engine | ✓ | ✓ | Partial | ✓ | Built |
| P6 XER Import/Export | ✓ | ✗ | ✗ | ✓ | Built |
| Modern Gantt UX | ✗ | Partial | ✓ | ✓ | Built |
| WBS Hierarchy | ✓ | ✓ | Partial | ✓ | 0 |
| Auto Quality Checks | ✗ | ✗ | ✗ | ✓ | 1 |
| One-Click Fix | ✗ | ✗ | ✗ | ✓ | 1 |
| Multi-Calendar | ✓ | ✓ | Partial | ✓ | 2 |
| Weather Integration | Partial | ✗ | Partial | ✓ | 2 |
| TIA / Fragnets | ✓ | Add-on | ✗ | ✓ | 3 |
| Narrative Reports | ✗ | ✗ | ✗ | ✓ | 3 |
| Resource Leveling | ✓ | ✓ | ✗ | ✓ | 4 |
| EVM Dashboard | ✓ | ✓ | ✗ | ✓ | 4 |
| AI Logic Detection | ✗ | ✗ | ✗ | ✓ | 5 |
| Delay Prediction | ✗ | ✗ | ✗ | ✓ | 5 |

SiteSync achieves full P6 parity by Phase 4, then surpasses it in Phase 5 with capabilities structurally impossible for a desktop app built in 2004. SiteSync can, because it was designed for this from the start.

# Success Metrics

Product Quality

- CPM Accuracy — Import 10 real P6 files. Dates and float match P6 within ±0.5 days on 100% of activities.

- Health Engine Precision — False positive rate <5%. Every flagged issue must be real.

- Performance — Full CPM recalc <500ms for 500 activities. Gantt at 60fps. XER import <3 seconds.

User Adoption

- Import Completion — >90% of XER imports result in viewing the Gantt.

- Health Check Engagement — >60% of users click at least one suggested fix.

- Return Rate — >3 schedule updates/week per active project.

Business Impact

- GC Conversion — 5 GCs using SiteSync as primary scheduler within 12 months of Phase 1.

- P6 Displacement — 2+ GCs fully replacing P6 within 18 months.

- Viral Adoption — Owners/CMs requiring GCs to submit via SiteSync for quality checks.

# The Bet

The construction industry runs on schedules. A .3 trillion market in the US alone, and the dominant tool is a Java desktop application from 2004. The interface hasn’t changed in 20 years. Every PM complains about it. No one has built a credible replacement because the CPM engine is genuinely hard.

SiteSync has already built the hard part—the engine works, the Gantt performs, the import pipeline handles real P6 files. What’s left is the intelligence layer that makes the switch not just possible but irresistible. A tool that checks your schedule. Warns about weather. Writes delay narratives. Knows from thousands of projects which links you forgot.

P6 can’t do any of that. By the time Oracle tries, SiteSync’s AI will have learned from every schedule that flows through the platform. That’s the compounding advantage. That’s the moat. That’s the bet.

“The people who are crazy enough to think they can change the industry are the ones who do.”