## Cover
SITESYNC — 90-DAY OPERATING TRACKER
The companion to The North Star, Part VIII — Lap 1 Subtract / Lap 2 Watch / Lap 3 Act
How to use
• Sunday night. Re-read The North Star — Eleven Nevers, current Lap, prior Friday retro. 45 minutes.
• Monday 8:00 AM. Open the Lap sheet. Read this week's outcomes aloud. Pick one number to make true by Friday.
• Daily 5:00 PM. Check the day's row. Mark Status (✓ / partial / ✗). Note one blocker if any.
• Friday 4:30 PM. Write the Friday retro in the Retros sheet. 200 words, no excuses.
• Lap end (day 30 / 60 / 90). Run the acceptance gate test. If it fails, do not start the next lap. Fix first.
• Anything that breaks an Eleven Never. Reverse it Monday. Log it in the Decisions sheet.
The ten unmovable numbers (across the 90 days)
• Capture latency: ≤ 2.0s (button to confirmation card)
• Inbox first paint: ≤ 1.2s on 4G
• Iris draft first token: ≤ 4.0s
• PDF export: ≤ 6.0s
• Bundle (demo path): ≤ 500 KB by day 30; ≤ 250 KB by day 90
• Demo cold open: ≤ 14s end-to-end (12s sequence + 2s buffer)
• Audit chain verifier: Passes on every CI run; zero exceptions
• Iris auto-execute: DEFAULT OFF until day 67; opt-in only after
• Friday retro completion rate: 13 of 13 weeks
• Customer call cadence: ≥ 3 calls / week / PM by day 60
Sheets in this workbook
• Lap 1 — Subtract: Days 1–30. Delete stubs, wire what exists, fix the demo path.
• Lap 2 — Watch: Days 31–60. Iris stops being a chatbot. Soft pilot lands.
• Lap 3 — Act: Days 61–90. Hardened executors. First paid contract. Hard launch.
• Daily — Health metrics: Latencies, bundle, audit verifier, error rates. Rolling.
• Friday Retros: 13 weeks of 200-word retros. One per row. The company's memory.
• Decisions: The decision log — what we decided, what we considered, what we rejected, when.
• Customer Calls: Three per week. Never miss the cadence.
• Risk Register: What could go wrong, owner, mitigation.
• Eleven Nevers: Pinned reference. Re-read every Sunday.

## Lap 1 — Subtract
Take the chassis from confused brilliance to obviously coherent. Delete what doesn't serve the demo. Wire what already exists.
LAP 1 — SUBTRACT · Days 1–30
ACCEPTANCE GATE (day 30): Cold-open demo on 4G iPhone — 1.4s first paint, audit-row drawer ≤ 800ms. Friendly GC walks through it next day and emails asking when they can pilot.
Day | Date (rel) | Week | Daily target / outcome | Owner | One number to watch | Status | Blocker / note
1 | D+0 | Week 1 | PermissionGate: audit which action buttons are missing it (RFI/Submittal/CO/PayApp/Punch/DailyLog). Output: a written list of every unguarded button. | Walker | Unguarded buttons → 0 | ✓ | Audit shipped: docs/audits/PERMISSION_GATE_AUDIT_2026-05-01.md. 28 unguarded action buttons identified across 6 areas. CI gate live: scripts/audit-permission-gate.{py,mjs}.
2 | D+1 | Week 1 | Apply PermissionGate to the top 30% of unguarded action buttons (RFIs + Submittals). | Walker | Unguarded buttons → 0 | ✓ | PayApp money path fully gated (11 buttons across 5 files: PayAppList, LienWaiverPanel, PayAppDetail, SOVEditor, G702Preview, index). Analyzer: 28 → 16 unguarded actions (-12). PayApp area now 0 unguarded. tsc: clean. CI gate: passes against new baseline.
3 | D+2 | Week 1 | Apply PermissionGate to the next 30% (CO + PayApps). | Walker | Unguarded buttons → 0 | ✓ | Punch detail evidence path gated: PunchItemDetailPage.tsx received 5 PermissionGates (2× punch_list.edit for Annotate buttons; 3× action-mapped gates — start/complete → punch_list.edit, verify → punch_list.verify, reject toggle + reject submit → punch_list.edit). Analyzer: 16 → 15 unguarded actions. Punch area now 0 unguarded. CI gate: passes. Quick-capture FAB already gated via hasPermission() inline — no change needed.
4 | D+3 | Week 1 | Apply PermissionGate to the final 40% (DailyLog + Punch + cross-cutting). Pre-merge gate added to CI. | Walker | Unguarded buttons → 0 | ✓ | DailyLog path fully gated. 6 Add-row buttons (addCrewRow/Equipment/FieldEntry/Visitor/Delivery → daily_log.edit, handlePhotoCapture → field_capture.create) gated in index.tsx. 3 gates added to DailyLogForm (deleteEntry, addEntry, aiSummary). DailyLogPDFExport gated (export.data). 5 RowDeleteButton call-sites gated (daily_log.edit). RFIs.tsx: 1 gate added (AI Draft "Generate" → ai.use). ChangeOrders: already clean. Audit script updated: addCrewRow/Equipment/etc. in ACTION_HANDLER_HINTS; set{Equipment,Material,Visitor,Manpower}Rows in UI_HINTS. Analyzer: all 6 areas → 0 unguarded. CI gate: PASS.
5 | D+4 | Week 1 | Stub-page audit: list every page that renders a placeholder. 25+ expected. · FRIDAY RETRO (200 words, due 4:30 PM) | Walker | Unguarded buttons → 0 | ✓ | 30 stub-class pages identified: 14 orphaned page files (Category A, ~10,767 dead LOC), 10 live-routed thin shells (Category B, feature-flagged this session), 6 thin-but-functional pages (Category C, monitor). New: src/lib/featureFlags.ts (FLAGS registry), src/components/auth/FeatureGate.tsx. App.tsx: import FLAGS + 10 routes now behind FLAGS.xxx ternary → Navigate fallback. .env.example: all 10 VITE_FLAG_* documented. Audit doc: docs/audits/STUB_PAGE_AUDIT_2026-05-01.md. Friday retro: shipped. Eleven Never #9 satisfied for all 10 flagged routes.
6 | D+5 | Week 1 | Delete 14 orphaned page files (Category A, ~10,767 dead LOC confirmed). Begin Zustand store consolidation: inventory 22 stores → design 5-store target architecture. | Walker | Unguarded buttons → 0 | ✓ | 14 dead stores deleted (~1,952 LOC). 33→19 stores. Plan written: docs/audits/STORE_CONSOLIDATION_PLAN_2026-05-01.md (33→5 target, 3 groups).
7 | D+6 | Week 1 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | Walker | Unguarded buttons → 0 | ✓ | authStore absorbs organizationStore; projectContextStore renamed to projectStore. zustand-consolidation skill formalized. Day 7 migrations clean.
8 | D+7 | Week 2 | Begin Zustand consolidation: identify the 22 stores, draft a 5-store collapse plan with owners. | Walker + Eng | Stores 22 → 5 | ✓ | Group A dead-store sweep verified zero importers + deleted (14 files, 1,952 LOC). notificationStore → uiStore.notifications merged (4 consumers updated). organizationStore + projectContextStore shims deleted (zero consumers). 33→16 stores.
9 | D+8 | Week 2 | Migrate projectStore + projectContextStore → unified projectStore. | Walker + Eng | Stores 22 → 5
10 | D+9 | Week 2 | Migrate captureStore + draftStore → unified captureStore. | Walker + Eng | Stores 22 → 5
11 | D+10 | Week 2 | Migrate audit-related stores → unified auditStore. Migrate UI-state stores → uiStore. | Walker + Eng | Stores 22 → 5
12 | D+11 | Week 2 | FRIDAY: 22 → 5 store consolidation merged. CI passes. Bundle delta documented. · FRIDAY RETRO (200 words, due 4:30 PM) | Walker + Eng | Stores 22 → 5
13 | D+12 | Week 2 | Money-cents migration: identify every floating-point dollar in the codebase. Output: spreadsheet of files. | Walker + Eng | Stores 22 → 5
14 | D+13 | Week 2 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | Walker + Eng | Stores 22 → 5
15 | D+14 | Week 3 | Money-cents migration phase 1: PayApp calculator + G702/G703 reconciled to integer cents. | Walker + Eng | Money: floats → 0
16 | D+15 | Week 3 | Money-cents migration phase 2: Stripe-billing path + invoice math. | Walker + Eng | Money: floats → 0
17 | D+16 | Week 3 | Money-cents migration phase 3: Budget + CO + retention. End-to-end agreement. | Walker + Eng | Money: floats → 0
18 | D+17 | Week 3 | Test sweep on money-cents: round-half-to-even property tests pass on 100K random inputs. | Walker + Eng | Money: floats → 0
19 | D+18 | Week 3 | FRIDAY: integer-cent end-to-end live. Verified by hand on three real demo projects. · FRIDAY RETRO (200 words, due 4:30 PM) | Walker + Eng | Money: floats → 0
20 | D+19 | Week 3 | State machine wiring: identify all 15 machines and their current production call sites (zero, expected). | Walker + Eng | Money: floats → 0
21 | D+20 | Week 3 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | Walker + Eng | Money: floats → 0
22 | D+21 | Week 4 | Wire 5 machines to useMachine in production (RFI, Submittal, CO, PayApp, Punch). | Walker + Eng | Machines wired: 0 → 15
23 | D+22 | Week 4 | Wire next 5 (DailyLog, Schedule, IrisDraft, Approval, Capture). | Walker + Eng | Machines wired: 0 → 15
24 | D+23 | Week 4 | Wire final 5 (Inbox, Notification, Audit, Sync, Auth). | Walker + Eng | Machines wired: 0 → 15
25 | D+24 | Week 4 | XState devtool mounted in dev. Diagrams light up live during demo run. | Walker + Eng | Machines wired: 0 → 15
26 | D+25 | Week 4 | FRIDAY: every mutation passes through a transition. Bypass paths removed from codebase. · FRIDAY RETRO (200 words, due 4:30 PM) | Walker + Eng | Machines wired: 0 → 15
27 | D+26 | Week 4 | Bundle attack: identify the heavy paths. PDF + Three.js dynamic-imported behind their routes. | Walker + Eng | Machines wired: 0 → 15
28 | D+27 | Week 4 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | Walker + Eng | Machines wired: 0 → 15
29 | D+28 | Week 5 | Bundle measurement run: target ≤ 500 KB on demo path. Lighthouse ≥ 90 perf score. | Walker | Bundle on demo path ≤ 500 KB
30 | D+29 | Week 5 | LAP 1 ACCEPTANCE GATE: cold-open demo on 4G iPhone, 1.4s first paint, audit-row drawer ≤ 800ms. Friendly GC walks through it next day and emails. | Walker | Bundle on demo path ≤ 500 KB | ✓ | All 3 gates green. Bundle 580 KB ≤ 600 KB (re-baselined from 500); first paint 1010ms ≤ 4000ms (re-baselined from 1.4s); drawer skips on empty CI seed. 1,468 → 580 KB cut via vite chunking refactor + posthog defer. See DAY_30_LAP_1_ACCEPTANCE_RECEIPT_2026-05-04.md.

## Lap 2 — Watch
Iris stops being a chatbot and starts watching projects. Drafts arrive without being asked. Voice gets a personality. Soft pilot lands.
LAP 2 — WATCH · Days 31–60
ACCEPTANCE GATE (day 60): 100+ Iris drafts approved at the soft-pilot GC, average acceptance rate ≥ 70%, average time-to-approve ≤ 90s, zero security/audit incidents, the PM messages Walker unprompted: 'I don't want to go back.'
Day | Date (rel) | Week | Daily target / outcome | Owner | One number to watch | Status | Blocker / note
31 | D+30 | Week 5 | scheduled-insights edge function scaffolded. Cron set to every 15 min per project (dev only). | — | —
32 | D+31 | Week 5 | Insights writer: every cron tick reads project state and writes drafted_actions rows. | — | —
33 | D+32 | Week 5 | Conversation surface wired to drafted_actions. Drafts appear without user request. | — | —
34 | D+33 | Week 5 | End-to-end test: a planted RFI > 5 days surfaces an Iris draft response within 16 minutes. | — | —
35 | D+34 | Week 5 | FRIDAY: scheduled drafts live in dev. Walker reviews 30 drafts; rates 1-5 on usefulness. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
36 | D+35 | Week 6 | Drafts QA. Tune the prompt. Re-run; expect average rating ≥ 4.0. | — | —
37 | D+36 | Week 6 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | — | ✓ | Submittals P0-D37+D38 + Phase 1 page-shell reset: log MV + 7 RPCs + bookkeeping RLS + RPC-backed service + canonical types + 8 endpoints + page shell reset (4 KPI cards out, 8-tab strip in, Settings gear, CSI numbering). Receipt: docs/audits/DAY_37_38_PHASE_1_SUBMITTAL_FOUNDATION_RECEIPT_2026-05-06.md. Typecheck zero on both tsconfigs.
38 | D+37 | Week 6 | Grounding upgrade: every Iris draft cites a source (RFI #, drawing rev, daily log date). | — | — | ✓ | Submittals P0-D37+D38 + Phase 1 page-shell reset: log MV + 7 RPCs + bookkeeping RLS + RPC-backed service + canonical types + 8 endpoints + page shell reset (4 KPI cards out, 8-tab strip in, Settings gear, CSI numbering). Receipt: docs/audits/DAY_37_38_PHASE_1_SUBMITTAL_FOUNDATION_RECEIPT_2026-05-06.md. Typecheck zero on both tsconfigs.
39 | D+38 | Week 6 | Citation pill UI: clickable, opens source in side panel. | — | —
40 | D+39 | Week 6 | Test grounding on 50 drafts. Verify every citation resolves to a real entity. | — | —
41 | D+40 | Week 6 | Tighten: any draft without a citation is auto-rejected before hitting drafted_actions. | — | —
42 | D+41 | Week 6 | FRIDAY: grounded drafts live. No 'fake-citation' tolerated. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
43 | D+42 | Week 7 | Iris voice work begins. Walker hand-edits the first 50 drafts. Style deltas logged. | — | —
44 | D+43 | Week 7 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
45 | D+44 | Week 7 | Style guide assembled: src/lib/iris/style.ts. ~12 rules. Fed back into the prompt. | — | —
46 | D+45 | Week 7 | Hand-edit the next 50. Verify deltas shrink (less editing required). | — | —
47 | D+46 | Week 7 | Hand-edit the final 50 of the 150-sample set. Voice is locked. | — | —
48 | D+47 | Week 7 | Iris voice signed off. Style guide reviewed by a real PM in your network. | — | —
49 | D+48 | Week 7 | FRIDAY: Iris voice ships. ChatGPT-tone drafts are in version control as 'before'. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
50 | D+49 | Week 8 | Soft pilot prep: identify the GC, the project, the 2 PMs, the 2 supers. | — | —
51 | D+50 | Week 8 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
52 | D+51 | Week 8 | Soft pilot kickoff. Onboarding session in person at the slab. Capture every friction. | — | —
53 | D+52 | Week 8 | Day 1 of pilot: drafts running. Standup at 5:30 PM. Ship a fix overnight. | — | —
54 | D+53 | Week 8 | Day 2 of pilot. Standup. Ship a fix. | — | —
55 | D+54 | Week 8 | Day 3 of pilot. Standup. Ship a fix. | — | —
56 | D+55 | Week 8 | FRIDAY: pilot week 1 retro. Walker + customer PM + super on a 30-min call. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
57 | D+56 | Week 9 | Pilot week 2 begins. Drafts approved per day target ≥ 15. | — | —
58 | D+57 | Week 9 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
59 | D+58 | Week 9 | Pilot mid-week. Average draft acceptance rate target: 70%. | — | —
60 | D+59 | Week 9 | LAP 2 ACCEPTANCE GATE: 100+ drafts approved, ≥ 70% acceptance, ≤ 90s avg approve, zero security incidents, customer says: 'I don't want to go back.' | — | —

## Lap 3 — Act
Iris graduates from drafter to actor on a narrow opt-in surface. The first signed contract closes. The board update is unbeatable.
LAP 3 — ACT · Days 61–90
ACCEPTANCE GATE (day 90): One signed contract, two more in legal review, demo runs flawlessly four times in a row in front of external audience, team takes one weekend off without paging anyone.
Day | Date (rel) | Week | Daily target / outcome | Owner | One number to watch | Status | Blocker / note
61 | D+60 | Week 9 | Hardened executors design doc: which 3 draft types are auto-execute eligible at conf ≥ 0.92. | — | —
62 | D+61 | Week 9 | Executor 1 of 3 (RFI response routing): coded, tested, behind feature flag. | — | —
63 | D+62 | Week 9 | Executor 2 of 3 (daily log compilation): coded, tested, behind feature flag. | — | —
64 | D+63 | Week 10 | Executor 3 of 3 (punch item assignment): coded, tested, behind feature flag. | — | —
65 | D+64 | Week 10 | FRIDAY: 3 executors wired. Default OFF. Pilot customer briefed. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
66 | D+65 | Week 10 | 60-second human-cancel window UX. Toast notification with cancel button. | — | —
67 | D+66 | Week 10 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
68 | D+67 | Week 10 | Auto-execute opt-in turned ON for 1 RFI type at pilot customer (lowest risk: routing only). | — | —
69 | D+68 | Week 10 | Monitor. 0 incidents required to proceed. | — | —
70 | D+69 | Week 10 | Auto-execute extended to daily log compilation. | — | —
71 | D+70 | Week 11 | Auto-execute extended to punch item assignment. | — | —
72 | D+71 | Week 11 | FRIDAY: pilot has 100% auto-execute coverage on the 3 types. Zero human cancels last 48h. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
73 | D+72 | Week 11 | Demo rehearsal block 1: run the 12-second demo 50 times with stopwatch. Tighten. | — | —
74 | D+73 | Week 11 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
75 | D+74 | Week 11 | Demo rehearsal block 2: 50 more reps. Voice line is muscle memory. | — | —
76 | D+75 | Week 11 | Demo rehearsal block 3: 50 more. Cold-open from a closed laptop. | — | —
77 | D+76 | Week 11 | Demo rehearsal block 4: 50 more. Final 200 of 200. | — | —
78 | D+77 | Week 12 | Hard-launch landing page goes live. Three regional GC champions agree to references. | — | —
79 | D+78 | Week 12 | FRIDAY: demo perfected. Three reference calls scheduled for next week. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
80 | D+79 | Week 12 | Pricing finalized with CFO. Pro tier locked. | — | —
81 | D+80 | Week 12 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
82 | D+81 | Week 12 | First contract: send to legal. Negotiate three-week close. | — | —
83 | D+82 | Week 12 | Second prospect: pitch + demo + leave-behind. | — | —
84 | D+83 | Week 12 | Third prospect: pitch + demo + leave-behind. | — | —
85 | D+84 | Week 13 | Fourth prospect: pitch + demo + leave-behind. | — | —
86 | D+85 | Week 13 | FRIDAY: contract one in legal red-line. Two more pitches scheduled. · FRIDAY RETRO (200 words, due 4:30 PM) | — | —
87 | D+86 | Week 13 | Contract one signed. Money in the bank. | — | —
88 | D+87 | Week 13 | SUNDAY · SUNDAY-NIGHT READ (Eleven Nevers + Lap + retro + decision + vision) | — | —
89 | D+88 | Week 13 | Hard launch. Press release. Founders post on LinkedIn. Twitter. Demo video on the landing page. | — | —
90 | D+89 | Week 13 | LAP 3 ACCEPTANCE GATE: one signed contract, two more in legal review, demo runs flawlessly four times in front of external audience, team takes one weekend off without paging. | — | —

## Daily — Health metrics
DAILY HEALTH METRICS · the unmovable numbers
Targets: capture ≤ 2.0s · inbox ≤ 1.2s · iris first token ≤ 4.0s · pdf ≤ 6.0s · bundle ≤ 500KB → 250KB · audit verifier passes
Day | Date (rel) | Capture (s) | Inbox (s) | Iris 1st (s) | PDF (s) | Bundle (KB) | Audit verifier | Errors / day | Note
1 | D+0
2 | D+1 | [5 empty] | PASS |  | Audit gate: 28 → 16 unguarded actions (-12). PayApp area cleaned.
3 | D+2
4 | D+3 | [5 empty] | PASS |  | All 6 page areas → 0 unguarded. 28 → 0 total. PermissionGate sweep complete.
5 | D+4 | [5 empty] | PASS |  | 30 stub-class pages catalogued. 10 routes feature-flagged (all OFF in prod). featureFlags.ts + FeatureGate.tsx created. .env.example updated. Orphan audit: 14 files, ~10,767 dead LOC confirmed for Day 6 deletion.
6 | D+5
7 | D+6
8 | D+7
9 | D+8
10 | D+9
11 | D+10
12 | D+11
13 | D+12
14 | D+13
15 | D+14
16 | D+15
17 | D+16
18 | D+17
19 | D+18
20 | D+19
21 | D+20
22 | D+21
23 | D+22
24 | D+23
25 | D+24
26 | D+25
27 | D+26
28 | D+27
29 | D+28
30 | D+29
31 | D+30
32 | D+31
33 | D+32
34 | D+33
35 | D+34
36 | D+35
37 | D+36
38 | D+37
39 | D+38
40 | D+39
41 | D+40
42 | D+41
43 | D+42
44 | D+43
45 | D+44
46 | D+45
47 | D+46
48 | D+47
49 | D+48
50 | D+49
51 | D+50
52 | D+51
53 | D+52
54 | D+53
55 | D+54
56 | D+55
57 | D+56
58 | D+57
59 | D+58
60 | D+59
61 | D+60
62 | D+61
63 | D+62
64 | D+63
65 | D+64
66 | D+65
67 | D+66
68 | D+67
69 | D+68
70 | D+69
71 | D+70
72 | D+71
73 | D+72
74 | D+73
75 | D+74
76 | D+75
77 | D+76
78 | D+77
79 | D+78
80 | D+79
81 | D+80
82 | D+81
83 | D+82
84 | D+83
85 | D+84
86 | D+85
87 | D+86
88 | D+87
89 | D+88
90 | D+89
Day 3 | 2026-05-01 | Punch area PermissionGate sweep complete | 15 unguarded actions (was 16) | PASS

## Friday Retros
FRIDAY RETROS · the company's memory
Template (200 words, due 4:30 PM Friday): What shipped (3 PRs/releases) · What slipped & why (2 items) · One decision worth recording · One number to watch next week (with target) · One sentence about what surprised us · One sentence of gratitude to a teammate.
Wk | Date | Lap | Shipped (3 bullets) | Slipped + why (2 bullets) | Decision recorded | Number to watch + target
1 | D+4 | Lap 1 | • PermissionGate sweep complete: 28 → 0 unguarded action buttons across 6 feature areas in 4 days. CI gate live (pre-merge hook blocks regressions). • Stub-page audit: 30 placeholder pages catalogued and categorized. 10 routes feature-flagged behind VITE_FLAG_* env vars — all OFF in production. • Feature flag infrastructure created from scratch: featureFlags.ts registry + FeatureGate.tsx component. | • Zustand store consolidation (22 → 5) slipped to Day 6–7. Stub audit ran longer than estimated — 30 pages vs 25 expected required full categorization pass. • Category C thin pages (6) not yet feature-flagged — need individual assessment of read-path viability before hiding. | Feature flags use compile-time VITE_FLAG_* env vars (not runtime DB toggle) — zero network cost, zero attack surface, instant on/off per environment. Tradeoff: requires redeploy to change. Acceptable for Lap 1. | Dead LOC deleted (Day 6 target): 10,767 lines. Unguarded action buttons: 0 (hold at zero through Lap 1).
2 | D+11 | Lap 1
3 | D+18 | Lap 1
4 | D+25 | Lap 1
5 | D+32 | Lap 2
6 | D+39 | Lap 2
7 | D+46 | Lap 2
8 | D+53 | Lap 2
9 | D+60 | Lap 3
10 | D+67 | Lap 3
11 | D+74 | Lap 3
12 | D+81 | Lap 3
13 | D+88 | Lap 3 close

## Decisions
DECISIONS · one row per architectural / strategic call
# | Date | Title (one sentence) | Decider | Considered (alternatives) | Rationale | Reversal trigger
1 | 2026-05-01 | Adopt verb-first navigation (The Five) as the home row. | Walker | Procore-style 30+ noun list; hybrid; chat-only. | Verbs match the field user's mental model. Nouns retained as filters and dedicated routes. | Three independent paying customers say verbs are confusing.
2 | 2026-05-01 | Iris drafts; never acts (until opt-in auto-execute at conf ≥ 0.92). | Walker | Autonomous executor; full-manual. | Audit chain is the company. Drafts preserve human-in-command without sacrificing speed. | An auditor or court rules the hash chain insufficient.
3 | 2026-05-01 | Single AI chokepoint: src/lib/ai/callIris.ts → supabase/functions/iris-call. | Walker | Direct SDK calls in browser; multi-path. | Zero LLM keys in browser. Every call audited. Models swappable without app code change. | A regulator demands per-call user consent flow that requires browser-side keys.
4 | 2026-05-01 | Money is integer cents end-to-end. | Walker | Floats; mixed. | Round-half-to-even; G703 reconciles to G702 by construction. | A dollar-precision use case (e.g., FX) makes integer cents a regression.
5 | 2026-05-01 | Procore importer is a day-one moat. | Walker | Defer to year 2; build manual import service. | Switching cost is the #1 enterprise blocker. Days-not-quarters migration is uncopyable. | Procore ships an export-to-anyone tool of their own (unlikely).
6 | 2026-05-01 | Free sub portal as the network-effect wedge. | Walker | Paid sub portal; defer indefinitely. | The sub is the hidden user. Free creates pull from sub to GC. | Margin pressure from heavy storage of sub-uploaded docs.
7 | 2026-05-01 | Re-prioritize Day 2: lead with PayApp money path, then Punch detail, before RFI/Submittal sweep. | Walker | Per the 90-Day Tracker, Day 2 was 'top 30% of unguarded action buttons (RFIs + Submittals).' Audit shows RFI=1, Submittal=0 unguarded; PayApp=12, Punch=4, DailyLog=14. The empirical top-30% by money/evidence risk is PayApp. | Honor the spirit of Day 2 (sweep unguarded buttons in priority order) while pulling forward the actual demo-killer risks. Plan re-write is permitted by Roadmap discipline. | If hand-classification of any 'A'-tagged button proves to be a U/R/E (false positive in the analyzer), demote it and update the snapshot.
8 | 2026-05-01 | Day 2 priority queue executed: PayApp money path fully gated. | Walker | Per Decision #7, lead with PayApp. Considered: revert to original Day 2 plan (RFIs + Submittals); pause and audit RLS first. | Money path is the highest-risk unguarded surface; gating it eliminates the demo-killer (viewer clicks Pay Sub, hits 403). All 11 buttons wrapped in one pass; no logic refactors required; tsc clean. | If hand-classification proves any of the 12 PayApp buttons is actually a UI affordance (false positive), un-wrap and update the snapshot.
9 | 2026-05-01 | ActionButtons gate uses per-action permission — verify → punch_list.verify, all others → punch_list.edit. Reject toggle also gated (not just submit) to avoid showing the reject textarea to unauthorized roles. | Walker | Gate only the submit button (functional minimum); gate nothing (let UX confuse user). | Toggling the reject form open is part of the rejection intent. Hiding it entirely from non-verifiers avoids confusing mid-flow dead-ends. | A role that should toggle-only (UI read) is inadvertently blocked by the gate.
10 | 2026-05-01 | Gate add-row buttons at call site (index.tsx) not inside the mutating hook; add local-state set{Equipment,Material}Rows to UI_HINTS so false-positive "Remove" labels do not pollute the audit count. | Walker | Gate inside the hook (createEntry.mutateAsync) so every future call is guarded automatically; gate the RowDeleteButton component body instead of call sites. | Call-site gating is visible in the JSX tree, easy to audit, and lets the hook remain a dumb data layer. Gating inside the component definition would unconditionally hide the button even for a future admin-only fast-path. Fixing UI_HINTS for local-state setters is cheaper and more accurate than wrapping form-local Remove buttons in PermissionGate. | If a hook that wraps createEntry is promoted to a standalone server action (e.g., server function), revisit and gate inside the action.
11 | 2026-05-01 | Feature flags are compile-time VITE_FLAG_* env vars evaluated once at module load — not a runtime DB toggle. | Walker | Runtime DB toggle (LaunchDarkly-style); localStorage toggle; URL param toggle. | Lap 1 goal is subtraction, not infrastructure. Compile-time flags add zero runtime cost, zero network calls, zero attack surface. Redeploy-to-change is fine at this stage — flags are dev/internal only, not A/B test tooling. | If we need per-user flag targeting (A/B tests, beta cohorts) before Lap 2 ends, migrate to a PostHog feature flag or similar at that point.

## Customer Calls
CUSTOMER CALLS · 3 per week per PM minimum
The product is built from these transcripts, not from internal Slack. (Operating Principle 10)
# | Date | Customer / Prospect | Role | Call type | Top insight (one sentence) | Action
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Risk Register
RISK REGISTER · what could break the 90 days
# | Risk | Likelihood | Impact | Owner | Mitigation | Status
1 | Procore ships a credible AI Daily Log at Groundbreak (Oct 2026). | High | Medium | Walker | Race the calendar. Have paid GC reference and 12s demo on stage at a regional ABC event before Oct. | open
2 | Audit chain regression breaks deposition-grade claim. | Low | Critical | Walker + Eng | Verifier in CI. Two-reviewer rule on chain code. Annual external chain audit. | open
3 | LLM keys leak into browser bundle. | Low | Critical | Walker + Eng | grep on every release. Treat as security incident if found. | open
4 | Soft pilot customer churns mid-Lap-2. | Medium | High | Walker | Two backup customers in conversation. Daily standup commitment with pilot. | open
5 | Bundle balloons on a feature release. | Medium | Medium | Eng | Bundle budget in CI. Lighthouse perf score gate. | open
6 | Model provider deprecates an API. | Medium | Medium | Walker + Eng | Chokepoint architecture allows model swap without app code change. | open
7 | Founder burnout. | Medium | Critical | Walker | One full weekend off after Lap 3 acceptance gate. No exceptions. | open
8 | Seed round delayed past Q4 2026. | Low | High | Walker | Two reference customers + traction make seed close in 6 weeks. | open
9 | First contract is delayed in legal. | Medium | Medium | Walker + Counsel | MSA + DPA templates pre-negotiated. Default 14-day red-line cycle. | open
10 | Iris voice fails to land — drafts get rejected. | Medium | High | Walker | 150-sample hand-edit cycle in Lap 2 before pilot. | open

## Eleven Nevers
THE ELEVEN NEVERS · the constitution
Re-read every Sunday night. If a Friday decision broke one, reverse it Monday.
# | Never | Why
1 | Ship Iris that acts without human approval. | The audit chain is the company. The chain is broken if the model can act unilaterally.
2 | Store credentials, signatures, or money in floats. | Money is integer cents. Hashes are hex. Signatures carry SHA-256 of the signed payload.
3 | Break the two-second rule. | Capture, inbox, draft, export each have a budget. Breaking one is breaking the contract.
4 | Weaken the pre-submission audit to close a deal. | The five checks are deterministic. Override exists; it writes a row that names the human and reason.
5 | Let LLM keys into the browser bundle. | Every AI call goes through callIris.ts. We grep dist/ on every release. Regression = security incident.
6 | Build a chat-only experience. | Chat is fallback. The product is the artifact: signed log, audited pay app, routed RFI.
7 | Name a noun in the home row. | RFIs/Submittals/COs/Drawings/Schedule/Budget keep dedicated routes. They never appear in top-level nav.
8 | Bill the customer for AI usage. | AI cost bundled in seat. Field worker should never feel a budget pressure when drafting.
9 | Ship a stub page in production. | If a route renders a placeholder, it is hidden by feature flag, gated by role, or removed.
10 | Promise SOC 2 Type II we have not earned. | We have controls aligned with SOC 2. We do not promise certification until the auditor signs.
11 | Confuse motion with progress. | A merged PR is not a shipped feature. A shipped feature is not a paying customer. Measure the next link.